TOR Billboards

GOVERNMENT OF PAKISTAN

EARTHQUAKE REHABILITATION AND RECONSTRUCTION A UTHORITY

******

PRWH Project

Quotations from Companies/Firms on Awareness

Campaign through Billboards/ Coverage to the Activities on Promotion of Rain water Harvesting (RWH) Project in Earthquake Affected areas (EQAAs) of AJK and KPK

Background:

In order to meet the water requirements, a sustainable, economically viable solution is required. Rain Water Harvesting is one of the best possible, viable alternative supplementary solutions.

To cope up with the future challenges of domestic water needs of EQAAs, ERRA has planned to promote the concept and techniques of Rooftop Rain Water Harvesting in EQAAs of KPK & AJK. A pilot project has been approved by ERRA and is being implemented through WatSan Sector of ERRA to popularize the initiative at large.

The Project aims to explore the opportunity meeting out immediate needs of water at house hold level to mitigate the water scarcity through taking advantage of natural resource of Rainwater and promoting the Concept of Rain Water Harvesting.

One of the key components of the Project is dissemination of information & techniques through Billboard’s in Earthquake Affected Areas of KPK and AJK.

Financial bids, on the basis of unit rates (per sft) are solicited from reputed Firms/companies on partnership basis for undertaking awareness campaign through billboards/hoardings coverage to the activities on Promotion of Rain Water Harvesting in Earthquake Affected areas of AJK and KPK  (location/rotational plan and size details attached as Annex-A). The firm may submit their Financial Proposals to the Project Coordinator RWH.

For any clarifications and further details please write or call Mr. Syed Fahad Qasim, Communication Officer RWH on following address;

Phone:	051-9030921

Address:	ERRA HQ, Main Murree Road, Opposite Margalla Town, Islamabad

e-mail:	fahad.qasim@erra.gov.pk

1.	Scope of the work

The scope of the work to be undertaken by the successful bidder in this regard would include but not limited to the following:

The intervention under this activity should result coverage to all RWH related activities carrying out in the EQAAs. The special task to be undertaken in this regard by the service provider may include, but not limited to:

      - Hiring of 19 billboards for nine months placed at the prominent point to be grad mutually of main city of district Abbottabad, Mansahra, Battagram, Shangla, Kohistan in KPK and Bagh, Muzaffarabad, Neelum, Rawlakot and Sadhnoti in AJK.

      - A quality skin of selected Photos along with messages would be pasted on hired billboards for nine months.

- Project Duration / Time Frame

      - The requisite billboards have to be installed within 15 days time with effect from the date of signing of the contract.

      - Each skin / message as to be replaced after every 2 months (as per approved plan).

- Eligibility criteria

  - National and International registered firms, or having NOC from the   Government of Pakistan (copy of registration certificate or NOC  along with sale tax registrations number and NTN number would be required to submit along with the proposal)

  - At least three years working experience in developing billboards. Firms having experience working in EQAAs would be given preference.

Annex-A

| Activity | Hoarding boards Plan of PRWH |
| --- | --- |
|  | Following Boards would be replaced on monthly rotational basis. Started date: |
| Sr. No. | District | Total Month | Total Boards | Size in Sft (RftxRft) | Board No | Rotation time line (Month)* |
|  |  |  |  |  |  | Oct | Nov | Dec | Jan | Feb | March | April | May | June |
| 1 | Abbottabad | 9 | 1 | 60X20 | 1 | 1 | 1 | 9 | 9 | 3 | 3 | 12 | 12 | 1 |
| 2 | Abbottabad | 9 | 1 | 10X20 | 2 | 2 | 2 | 19 | 19 | 8 | 8 | 13 | 13 | 2 |
| 3 | Mansehra | 9 | 1 | 60X20 | 3 | 3 | 3 | 12 | 12 | 14 | 14 | 1 | 1 | 3 |
| 4 | Mansehra | 9 | 1 | 10X20 | 4 | 4 | 4 | 17 | 17 | 15 | 15 | 16 | 16 | 4 |
| 5 | Mansehra | 9 | 1 | 10X20 | 5 | 5 | 5 | 18 | 18 | 7 | 7 | 8 | 8 | 5 |
| 6 | Battgram | 9 | 1 | 10X20 | 6 | 6 | 6 | 14 | 14 | 13 | 13 | 17 | 17 | 6 |
| 7 | Kohistan | 9 | 1 | 10X20 | 7 | 7 | 7 | 13 | 13 | 19 | 19 | 14 | 14 | 7 |
| 8 | Shangla | 9 | 1 | 10X20 | 8 | 8 | 8 | 15 | 15 | 17 | 17 | 11 | 11 | 8 |
| 9 | Muzaffarabad | 9 | 1 | 90X30 | 9 | 9 | 9 | 1 | 1 | 9 | 9 | 3 | 3 | 9 |
| 10 | Muzaffarabad | 9 | 1 | 10X20 | 10 | 10 | 10 | 4 | 4 | 6 | 6 | 7 | 7 | 10 |
| 11 | Muzaffarabad | 9 | 1 | 10X20 | 11 | 11 | 11 | 2 | 2 | 4 | 4 | 5 | 5 | 11 |
| 12 | Neelum | 9 | 1 | 60X20 | 12 | 12 | 12 | 3 | 3 | 1 | 1 | 9 | 9 | 12 |
| 13 | Neelum | 9 | 1 | 10X20 | 13 | 13 | 13 | 6 | 6 | 2 | 2 | 4 | 4 | 13 |
| 14 | Bagh | 9 | 1 | 10X20 | 14 | 14 | 14 | 7 | 7 | 16 | 16 | 10 | 10 | 14 |
| 15 | Bagh | 9 | 1 | 10X20 | 15 | 15 | 15 | 8 | 8 | 19 | 19 | 18 | 18 | 15 |
| 16 | Bagh | 9 | 1 | 10X20 | 16 | 16 | 16 | 10 | 10 | 5 | 5 | 2 | 2 | 16 |
| 17 | Rawalakot | 9 | 1 | 10X20 | 17 | 17 | 17 | 11 | 11 | 10 | 10 | 6 | 6 | 17 |
| 18 | Rawalakot | 9 | 1 | 10X20 | 18 | 18 | 18 | 12 | 12 | 11 | 11 | 15 | 15 | 18 |
| 19 | Sudhnoti | 9 | 1 | 10X20 | 19 | 19 | 19 | 16 | 16 | 12 | 12 | 18 | 18 | 19 |

* Any change in Rotation time line will be informed at the time of installation.

# Text boxes

Note: Panaflex Specification (Media 440 gms)